## Sheet1
test_id | test_name | status | priority | execution_time | environment | assignee | comments | defect_severity | defect_type | impact | likelihood | detection_phase | root_cause | defect_status | defect_id | business_impact
TEST_0001 | Payment Gateway Integration | fail | critical | 120 | production | Security Team | Payment processing fails with timeout errors | Critical | Functional | High | Very Likely | Production | Third Party | Open | CRIT_001 | Revenue loss - customers cannot complete purchases
TEST_0002 | User Authentication Security | fail | critical | 90 | production | Security Team | Authentication bypass vulnerability discovered | Critical | Security | High | Very Likely | Security Testing | Design Flaw | Open | CRIT_002 | Security breach risk - unauthorized access possible
TEST_0003 | Database Transaction Rollback | fail | high | 150 | staging | Database Team | Transaction rollback mechanism not working | Medium | Functional | Medium | Likely | System Testing | Code Logic Error | Open | MED_001 | Feature limitation - reduced functionality
TEST_0004 | API Rate Limiting | pass | medium | 45 | staging | API Team | Rate limiting correctly implemented
TEST_0005 | Data Encryption Validation | fail | critical | 180 | production | Security Team | Encryption algorithm shows weakness | Medium | UI | Low | Very Likely | Security Testing | Design Flaw | In Progress | MED_002 | User experience issue - interface problems
TEST_0006 | Session Management | blocked | critical | 0 | production | DevOps Team | Environment unavailable for testing | Blocked | Infrastructure | High | Very Likely | Production | Environment | Blocked | BLOCK_001 | Testing blocked - cannot verify critical functionality
TEST_0007 | File Upload Security | fail | high | 75 | staging | Security Team | File upload allows malicious content | Medium | Performance | Medium | Likely | Security Testing | Configuration Issue | Open | MED_003 | Slow response time - performance degradation
TEST_0008 | SQL Injection Prevention | fail | critical | 110 | production | Security Team | SQL injection vulnerability found | Minor | Cosmetic | Low | Very Likely | Security Testing | Code Logic Error | Open | MIN_001 | Visual inconsistency - minor display issue
TEST_0009 | Cross-Site Scripting Protection | pass | medium | 60 | staging | Frontend Team | XSS protection working correctly
TEST_0010 | Performance Under Load | fail | high | 200 | production | Performance Team | System crashes under 1000 concurrent users |  |  |  | Very Likely | Performance Testing | Code Logic Error
TEST_0011 | Data Backup Verification | blocked | critical | 0 | production | DevOps Team | Backup system completely down |  |  |  | Very Likely | Production | Environment
TEST_0012 | Password Policy Enforcement | fail | high | 95 | staging | Security Team | Password policy not enforced for admin users |  |  |  | Possible | System Testing | Requirements Gap
TEST_0013 | Two-Factor Authentication | pass | medium | 55 | staging | Security Team | 2FA working as expected
TEST_0014 | Audit Log Generation | fail | critical | 130 | production | Audit Team | Critical security events not logged |  |  |  | Very Likely | Production | Configuration Issue
TEST_0015 | System Recovery Testing | blocked | critical | 0 | production | Infrastructure Team | Recovery process fails completely |  |  |  | Very Likely | Production | Environment